## Cover Page
GROUP 01
Project on Artificial Intelligence
Project Work Breakdown Structure
Query-Adaptive Retrieval Fusion for Visual RAG over PDF and Image Documents
ID | Full Name
23110035 | Trần Đình Khương
23110052 | Bùi Trần Tấn Phát
23110060 | Trần Huỳnh Xuân Thanh

## WBS (hidden)
T2
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Not Started
| Group |  |  | 01
| Project Topic |  |  | QPAF — Query-Page Adaptive Fusion for Visual Document Retrieval
| Task |  |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5 | [6 empty] | W6 | [6 empty] | W7 | [6 empty] | W8 | [6 empty] | W9 | [6 empty] | W10 | [6 empty] | W11 | [6 empty] | W12 | [6 empty] | W13 | [6 empty] | W14 | [6 empty] | W15 | [6 empty] | W16
[10 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56 | D57 | D58 | D59 | D60 | D61 | D62 | D63 | D64 | D65 | D66 | D67 | D68 | D69 | D70 | D71 | D72 | D73 | D74 | D75 | D76 | D77 | D78 | D79 | D80 | D81 | D82 | D83 | D84 | D85 | D86 | D87 | D88 | D89 | D90 | D91 | D92 | D93 | D94 | D95 | D96 | D97 | D98 | D99 | D100 | D101 | D102 | D103 | D104 | D105 | D106 | D107 | D108 | D109 | D110 | D111 | D112
 | time axis 2026-08-24 to 2026-12-13
|  | 1. |  | Literature & Scope | 2026-08-24 | 2026-09-06 | All members | M1 — Scope/RQs/protocol/evidence matrix frozen | Not Started | bar: 2026-08-24 to 2026-09-06
|  |  | 1.1. | Freeze research scope, novelty boundary, RQ1–RQ4/H1–H5, benchmark hierarchy and mandatory experiments | 2026-08-24 | 2026-08-27 | Khương + Thanh + Phát | Frozen scope; RQs/hypotheses; mandatory-vs-optional experiment list | Not Started
|  |  | 1.2. | Define controlled experimental protocol: official splits, fixed factors, Top-K, normalization, metrics and success criteria | 2026-08-24 | 2026-08-30 | Khương + Phát | Experiment protocol; nDCG/Recall/MRR/efficiency specification; control checklist | Not Started
|  |  | 1.3. | Review ColPali, VisRAG, MMDocIR, SimpleDoc, visual/multimodal retrieval, fusion and recent VDR efficiency methods | 2026-08-31 | 2026-09-06 | Phát + Thanh + Khương | Literature matrix covering baselines, datasets, methods, results and limitations | Not Started
|  |  | 1.4. | Build evidence matrix, reference library and citation-traceability process for all major research claims | 2026-09-01 | 2026-09-05 | Phát + Khương | Evidence matrix; reference list; citation audit checklist | Not Started
|  |  | 1.5. | Verify dataset/model licenses, privacy/ethical constraints and reproducibility repository structure | 2026-09-03 | 2026-09-06 | Thanh + Phát | License/ethics notes; reproducibility folder skeleton; logging/privacy rules | Not Started
|  | 2. |  | Dataset & Baseline Setup | 2026-09-07 | 2026-09-20 | All members | M2 — ViDoRe pipeline + BM25/Dense/Visual baselines operational | Not Started | bar: 2026-09-07 to 2026-09-20
|  |  | 2.1. | Acquire and inspect ViDoRe official split; prepare MMDocIR plus optional DocVQA/MP-DocVQA/ViOCRVQA/ReceiptVQA manifests | 2026-09-07 | 2026-09-10 | Thanh + Phát | Dataset manifests; official split mapping; no custom benchmark/annotation | Not Started
|  |  | 2.2. | Implement retrieval evaluation harness and experiment logging for nDCG@K, Recall@K, MRR, latency, memory and index size | 2026-09-07 | 2026-09-12 | Khương + Thanh | Evaluation scripts; metric tests; experiment metadata schema | Not Started
|  |  | 2.3. | Implement preprocessing architecture: native PDF text first, OCR fallback for scans/images, page rendering and versioned metadata | 2026-09-08 | 2026-09-13 | Thanh + Khương | Canonical text + page-image representation; parser/OCR/rendering pipeline; metadata versions | Not Started
|  |  | 2.4. | Implement frozen retriever architecture: BM25 lexical index, multilingual dense text index, and ColPali/ColQwen-style visual page index | 2026-09-14 | 2026-09-19 | Khương + Thanh + Phát | Three retrievers/indexes with frozen pretrained backbones and reproducible configs | Not Started
|  |  | 2.5. | Create common Top-K retrieval interface and run smoke tests so all three retrievers execute on the same ViDoRe subset/protocol | 2026-09-18 | 2026-09-20 | All members | Unified retrieval outputs; baseline smoke-test table; Milestone 1 evidence | Not Started
|  | 3. |  | Proposed Method — QARF | 2026-09-21 | 2026-10-18 | Khương + Thanh | M3 — QARF runs end to end with validation results | Not Started | bar: 2026-09-21 to 2026-10-18
|  |  | 3.1. | Analyze retriever score distributions, confidence, Top-K overlap/disagreement and representative failure cases | 2026-09-21 | 2026-09-27 | Khương + Thanh + Phát | Score/overlap analysis; complementarity evidence for RQ2; error inspection notes | Not Started
|  |  | 3.2. | Implement score normalization, Reciprocal Rank Fusion and fixed weighted score fusion; tune only on validation and freeze weights | 2026-09-28 | 2026-10-04 | Khương + Phát | RRF baseline; normalized fixed-fusion baseline; frozen validation-selected weights | Not Started
|  |  | 3.3. | Implement QARF independent retrieval + candidate union and query features: length, numeric ratio, date/currency/ID indicators, punctuation, quotes and IDF | 2026-10-05 | 2026-10-09 | Khương + Thanh | Candidate-union module; query-feature extractor | Not Started
|  |  | 3.4. | Implement retrieval-confidence and agreement features: top score, margin, variance, entropy and pairwise Top-K overlap; implement lightweight gating candidates | 2026-10-05 | 2026-10-11 | Thanh + Khương | Confidence/agreement features; linear/regressor + shallow MLP; optional tree-based gate; no LLM router | Not Started
|  |  | 3.5. | Implement softmax per-query weights and final ranking over the candidate union; run QARF prototype and validation experiments | 2026-10-12 | 2026-10-18 | Khương + Thanh + Phát | End-to-end QARF; alpha/beta/gamma per query; validation metrics; Milestone 2 evidence | Not Started
|  | 4. |  | Experiments & Ablation | 2026-10-19 | 2026-11-15 | All members | M4 — Quantitative evidence sufficient to answer RQ1 and select production retrieval | Not Started | bar: 2026-10-19 to 2026-11-15
|  |  | 4.1. | Run E1 final ViDoRe experiments for BM25, dense and visual individual retrievers under the frozen protocol | 2026-10-19 | 2026-10-25 | Khương + Thanh + Phát | Final individual-baseline nDCG/Recall/MRR and efficiency table | Not Started
|  |  | 4.2. | Run E2 static fusion and E3 QARF: compare best individual vs RRF/fixed fusion vs QARF with only fusion strategy changed | 2026-10-26 | 2026-11-01 | All members | Main controlled-comparison table; query-level outputs; RQ1 primary evidence | Not Started
|  |  | 4.3. | Run ablations: A1 fixed-vs-adaptive and A2 without visual (mandatory); A3 without lexical, A4 query-only, A5 retrieval-only if time permits | 2026-11-02 | 2026-11-08 | Khương + Thanh + Phát | Mandatory ablation report plus optional feature/modality ablations | Not Started
|  |  | 4.4. | Measure accuracy–efficiency trade-off and statistical validity: mean/p95 latency, GPU memory, index size, QARF overhead, paired/bootstrap/effect-size analysis | 2026-11-09 | 2026-11-13 | Khương + Thanh | Efficiency profile; confidence intervals/effect size; per-domain results where available | Not Started
|  |  | 4.5. | Run MMDocIR external validation if feasible; perform query-type/error analysis; apply decision gate to choose QARF or strongest static fusion for the application | 2026-11-09 | 2026-11-15 | All members | MMDocIR validation or constrained matrix; error taxonomy; production architecture decision record | Not Started
|  | 5. |  | Application | 2026-11-16 | 2026-11-29 | Phát + Thanh | M5 — Working Vietnamese-oriented PDF/Image Visual RAG application | Not Started | bar: 2026-11-16 to 2026-11-29
|  |  | 5.1. | Freeze the production architecture after E1–E3 and implement ingestion: upload, file-type validation, hash/versioning, extraction, rendering and OCR fallback | 2026-11-16 | 2026-11-20 | Phát + Thanh | Production architecture record; PDF/PNG/JPG ingestion pipeline | Not Started
|  |  | 5.2. | Implement BM25/dense/visual indexing jobs, model orchestration, caching/logging and retrieval API exposing lexical/dense/visual/fusion scores | 2026-11-16 | 2026-11-22 | Phát + Khương + Thanh | Indexing service; retrieval API; score/provenance payload; cache/logging | Not Started
|  |  | 5.3. | Integrate selected QARF/best method → relevant pages → fixed existing answer model using question, Top-K pages, extracted text and optional page images | 2026-11-23 | 2026-11-26 | Phát + Khương | End-to-end retrieval-to-answer service with fixed answerer | Not Started
|  |  | 5.4. | Implement evidence presentation and frontend: answer, source document/page/image, retrieval score, relevant text and optional bbox only when parser coordinates exist | 2026-11-23 | 2026-11-29 | Phát + Thanh | Upload → Index → Ask → Retrieve → Answer → Show Source UI; evidence metadata display | Not Started
|  |  | 5.5. | Validate Vietnamese application on ViOCRVQA and ReceiptVQA plus small demo PDFs; run optional E5 downstream QA on DocVQA/MP-DocVQA if time permits | 2026-11-26 | 2026-11-29 | All members | Vietnamese/structured-document validation; optional downstream-QA comparison; demo cases | Not Started
|  | 6. |  | Report & Reproducibility | 2026-11-30 | 2026-12-13 | All members | M6 — Research + application + report + presentation + demo completed | Not Started | bar: 2026-11-30 to 2026-12-13
|  |  | 6.1. | Run end-to-end/system testing and consolidate final figures, tables, latency/stability results and demo-quality application build | 2026-11-30 | 2026-12-04 | All members | System test report; final result figures/tables; polished demo build | Not Started
|  |  | 6.2. | Complete reproducibility package: configs, datasets, preprocessing, indexes, retrievers, fusion, experiments, results, figures, application, references and README | 2026-11-30 | 2026-12-06 | Khương + Thanh + Phát | Reproducibility repository; experiment IDs/versions/seeds/hardware/runtime/metrics | Not Started
|  |  | 6.3. | Perform citation audit, dataset/model license review, privacy/ethical checks and freeze final test results plus production configuration | 2026-12-03 | 2026-12-06 | Phát + Khương | Citation/license/privacy checklist; frozen final results/configuration | Not Started
|  |  | 6.4. | Complete final report using actual results; document limitations/future work and clearly separate QARF research contribution from engineering/application contributions | 2026-12-07 | 2026-12-11 | All members | Final five-chapter report; conclusions tied to quantitative evidence | Not Started
|  |  | 6.5. | Prepare presentation, demo script, defense rehearsal and final submission; ensure all members understand RQs, hypotheses, baselines, QARF, metrics and main result | 2026-12-07 | 2026-12-13 | All members | Presentation deck; demo script; rehearsal notes; final defense/submission package | Not Started
[5 empty] | 2025-08-09 | 2025-05-10

## Milestones
T2
MILESTONE
[9 empty] | Done |  | Deferred
[9 empty] | In Progress |  | Contingency
Blocked
| Schedule: 16 weeks — 24/08/2026 to 13/12/2026 | [7 empty] | Not Started
| Group |  |  | 01
| Project Topic |  |  | QPAF — Query-Page Adaptive Fusion for Visual Document Retrieval
| Task |  |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5 | [6 empty] | W6 | [6 empty] | W7 | [6 empty] | W8 | [6 empty] | W9 | [6 empty] | W10 | [6 empty] | W11 | [6 empty] | W12 | [6 empty] | W13 | [6 empty] | W14 | [6 empty] | W15 | [6 empty] | W16
[10 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56 | D57 | D58 | D59 | D60 | D61 | D62 | D63 | D64 | D65 | D66 | D67 | D68 | D69 | D70 | D71 | D72 | D73 | D74 | D75 | D76 | D77 | D78 | D79 | D80 | D81 | D82 | D83 | D84 | D85 | D86 | D87 | D88 | D89 | D90 | D91 | D92 | D93 | D94 | D95 | D96 | D97 | D98 | D99 | D100 | D101 | D102 | D103 | D104 | D105 | D106 | D107 | D108 | D109 | D110 | D111 | D112
 | time axis 2026-09-14 to 2027-01-03
|  | M1 |  | Repository Audit, Reproducibility & Protocol Freeze | 2026-09-14 | 2026-09-27 | Tấn Phát | Trusted starting-state record and frozen protocol package Dependency: G1 | In Progress | bar: 2026-09-14 to 2026-09-16
|  |  | M1.1 | Reconcile W7/W66 oracle evidence and claim boundary | 2026-09-08 | 2026-09-10 | Thanh | W7/W66 per-query review, 95% CI, W/T/L and oracle-only wording | Done | bar: 2026-09-15 to 2026-09-17
|  |  | M1.2 | Verify the local QARF/QPAF method core | 2026-09-09 | 2026-09-10 | Tấn Phát | Passing 13-feature, gate, fusion, loss and gradient checks | Done | bar: 2026-09-18 to 2026-09-20
|  |  | M1.3 | Verify the primary-corpus audit package and closed boundary | 2026-09-10 | 2026-09-11 | Khương | Hash-valid CPU audit package; execution remains unauthorized | Done | bar: 2026-09-16 to 2026-09-20
|  |  | M1.4 | Audit repository and research artifacts | 2026-09-11 | 2026-09-16 | Khương | Repository, data, config, run and Git inventory with hashes and gaps | In Progress | bar: 2026-09-14 to 2026-09-16
|  |  | M1.5 | Freeze experiment protocol and governance | 2026-09-16 | 2026-09-18 | Tấn Phát | Approved task graph, splits, metrics, seeds, baselines and run policy | Blocked | bar: 2026-09-16 to 2026-09-18
|  |  | M1.6 | Run and review the primary-corpus collision audit | 2026-09-21 | 2026-09-22 | Khương | Reviewed page/alias manifest with zero content collisions | Blocked | bar: 2026-09-21 to 2026-09-22
|  |  | M1.7 | Freeze experiment registry and test policy | 2026-09-21 | 2026-09-23 | Thanh | Append-only ledger schema, naming rules and test classification | Not Started | bar: 2026-09-21 to 2026-09-23
|  |  | M1.8 | Prepare OCR calibration and artifact namespaces | 2026-09-22 | 2026-09-23 | Khương | OCR checklist, failure thresholds and create-once output plan | Not Started | bar: 2026-09-22 to 2026-09-23
|  |  | M1.9 | G1 — Reproducibility: can the team trust the evidence and protocol? | 2026-09-24 | 2026-09-25 | Tấn Phát | PASS / PARTIAL / BLOCKED / FAIL record for evidence and protocol readiness Dependency: Các Task M1 | Blocked | bar: 2026-09-24 to 2026-09-25
|  |  | M1.10 | R1 — Sprint 1 Progress Report | 2026-09-24 | 2026-09-25 | Tấn Phát | Supervisor progress report + evidence + blockers + next sprint plan Dependency: G1 | Not Started | bar: 2026-09-24 to 2026-09-25
|  | M2 |  | Final Diagnostics & Learned Experiment Readiness | 2026-09-28 | 2026-10-11 | Khương | Verified retrieval cache and matched learned-pilot package Dependency: D1 | Blocked | bar: 2026-09-28 to 2026-10-11
|  |  | M2.1 | Freeze data-split roles and ID manifests | 2026-09-28 | 2026-09-30 | Thanh | Train/validation/confirmation/external ID manifests; zero overlap Dependency: G1 | Not Started | bar: 2026-09-28 to 2026-09-30
|  |  | M2.2 | Calibrate BM25, BGE-M3, and visual retrieval | 2026-09-28 | 2026-09-30 | Khương | Pinned 3-retriever smoke test, parity checks and resource caps Dependency: G1 | Not Started | bar: 2026-09-28 to 2026-09-30
|  |  | M2.3 | Calibrate pinned OCR on a bounded sample | 2026-10-01 | 2026-10-02 | Khương | OCR runtime, quality and failure calibration; full-run threshold Dependency: G1 | Not Started | bar: 2026-10-01 to 2026-10-02
|  |  | M2.4 | Build the minimal learned training/evaluation pipeline | 2026-09-28 | 2026-10-02 | Tấn Phát | Tested dataset, trainer, evaluator, checkpoint, telemetry and failure paths Dependency: G1 | Not Started | bar: 2026-09-28 to 2026-10-02
|  |  | M2.5 | Freeze baselines, statistics, and leakage checks | 2026-10-01 | 2026-10-05 | Thanh | Frozen baseline roster; paired 10,000-bootstrap CI and W/T/L fixtures Dependency: G1 | Not Started | bar: 2026-10-01 to 2026-10-05
|  |  | M2.6 | Run full OCR and verify page-level hashes | 2026-10-05 | 2026-10-06 | Khương | Complete OCR bundle with page hashes and explicit failures Dependency: G1 | Not Started | bar: 2026-10-05 to 2026-10-06
|  |  | M2.7 | Prepare matched QARF/QPAF configs | 2026-10-05 | 2026-10-07 | Tấn Phát | Shared-base configs; semantic diff limited to gate granularity Dependency: G1 | Not Started | bar: 2026-10-05 to 2026-10-07
|  |  | M2.8 | Build verified 3-retriever cache and candidate pool | 2026-10-07 | 2026-10-08 | Khương | Scores, top-200 lists and ≤600-page unions; recall ≥0.95, zero uncovered Dependency: G1 | Not Started | bar: 2026-10-07 to 2026-10-08
|  |  | M2.9 | Run bounded CARF diagnostic or close as not run | 2026-10-06 | 2026-10-08 | Thanh | CARF K=3 result with K=2/4 sensitivity, or justified not-run record Dependency: G1 | Deferred | bar: 2026-10-06 to 2026-10-08
|  |  | M2.10 | Audit data and learned-pilot readiness | 2026-10-08 | 2026-10-09 | Thanh | Independent review of hashes, coverage, splits, tests, config parity and reload Dependency: G1 | Not Started | bar: 2026-10-08 to 2026-10-09
|  |  | M2.11 | D1 — Data Readiness: is the matched pilot package valid? | 2026-10-09 | 2026-10-09 | Thanh | PASS / PARTIAL / BLOCKED / FAIL record for executable pilot readiness Dependency: Các Task M2 | Not Started | bar: 2026-10-09
|  |  | M2.12 | R2 — Sprint 2 Progress Report | 2026-10-08 | 2026-10-09 | Tấn Phát | Supervisor progress report + evidence + blockers + next sprint plan Dependency: D1 | Not Started | bar: 2026-10-08 to 2026-10-09
|  | M3 |  | Matched Learned QARF vs QPAF Pilot | 2026-10-12 | 2026-10-25 | Tấn Phát | Valid matched QARF–QPAF pilot and learned-viability decision Dependency: G2 | Blocked | bar: 2026-10-12 to 2026-10-25
|  |  | M3.1 | Seal pilot inputs and verify row parity | 2026-10-12 | 2026-10-13 | Khương | Immutable cache/splits with identical rows, order, features and qrels Dependency: D1 | Not Started | bar: 2026-10-12 to 2026-10-13
|  |  | M3.2 | Run the matched learned QARF pilot | 2026-10-14 | 2026-10-16 | Tấn Phát | Approved QARF checkpoint, predictions, manifest and telemetry Dependency: D1 | Blocked | bar: 2026-10-14 to 2026-10-16
|  |  | M3.3 | Independently validate the QARF run | 2026-10-19 | 2026-10-20 | Thanh | Recomputed metrics/provenance and reload parity within 1e-7 Dependency: D1 | Not Started | bar: 2026-10-19 to 2026-10-20
|  |  | M3.4 | Run the matched learned QPAF pilot | 2026-10-21 | 2026-10-22 | Tấn Phát | Approved matched QPAF checkpoint, predictions, manifest and telemetry Dependency: D1 | Blocked | bar: 2026-10-21 to 2026-10-22
|  |  | M3.5 | Compare QPAF and QARF per query | 2026-10-22 | 2026-10-23 | Thanh | QPAF–QARF per-query deltas, 95% CI, W/T/L, concentration and failures Dependency: D1 | Not Started | bar: 2026-10-22 to 2026-10-23
|  |  | M3.6 | Verify output integrity and resource gates | 2026-10-22 | 2026-10-23 | Khương | Finite-output, reload, latency, memory and telemetry review Dependency: D1 | Not Started | bar: 2026-10-22 to 2026-10-23
|  |  | M3.7 | G2 — Learned Viability: does learned QPAF outperform matched QARF? | 2026-10-23 | 2026-10-23 | Tấn Phát | GO / PARTIAL–INVESTIGATE / NO-GO–PIVOT / BLOCKED matched learned decision Dependency: Các Task M3 | Blocked | bar: 2026-10-23
|  |  | M3.8 | R3 — Sprint 3 Progress Report | 2026-10-22 | 2026-10-23 | Tấn Phát | Supervisor progress report + evidence + blockers + next sprint plan Dependency: G2 | Not Started | bar: 2026-10-22 to 2026-10-23
|  | M4 |  | Main Method Decision & Full Baseline Evaluation | 2026-10-26 | 2026-11-08 | Thanh | Fair baseline table and frozen main-method direction Dependency: G2A | Not Started | bar: 2026-10-26 to 2026-11-08
|  |  | M4.1 | Freeze confirmation access and evaluation hashes | 2026-10-26 | 2026-10-27 | Thanh | Sealed confirmation data plus method, checkpoint and evaluation manifest Dependency: G2 | Not Started | bar: 2026-10-26 to 2026-10-27
|  |  | M4.2 | Freeze baseline inputs and train-only settings | 2026-10-26 | 2026-10-28 | Khương | Shared baseline bundle with audited static/RRF train-only fitting Dependency: G2 | Not Started | bar: 2026-10-26 to 2026-10-28
|  |  | M4.3 | Execute the frozen G2 branch | 2026-10-28 | 2026-11-02 | Tấn Phát | Frozen QPAF, one preregistered revision, or documented negative-result pivot Dependency: G2 | Not Started | bar: 2026-10-28 to 2026-11-02
|  |  | M4.4 | Run the full deployable baseline evaluation | 2026-11-03 | 2026-11-05 | Tấn Phát | Predictions and fair baseline table with oracle rows separated Dependency: G2 | Not Started | bar: 2026-11-03 to 2026-11-05
|  |  | M4.5 | Audit baseline fairness and uncertainty | 2026-11-05 | 2026-11-06 | Thanh | Independent train-only, paired-delta, tie, hash and uncertainty review Dependency: G2 | Not Started | bar: 2026-11-05 to 2026-11-06
|  |  | M4.6 | Freeze the main-method direction | 2026-11-06 | 2026-11-06 | Tấn Phát | continue_qpaf / revise_once / negative_qpaf_result decision Dependency: G2 | Not Started | bar: 2026-11-06
|  |  | M4.7 | G2A — Main Method Direction: freeze the robustness path | 2026-11-06 | 2026-11-06 | Tấn Phát | Frozen method/config, checkpoints and remaining experiment roster Dependency: Các Task M4 | Not Started | bar: 2026-11-06
|  |  | M4.8 | R4 — Sprint 4 Progress Report | 2026-11-05 | 2026-11-06 | Tấn Phát | Supervisor progress report + evidence + blockers + next sprint plan Dependency: G2A | Not Started | bar: 2026-11-05 to 2026-11-06
|  | M5 |  | Ablation, Robustness & Generalization | 2026-11-09 | 2026-11-22 | Thanh | Three-seed robustness, key ablations, efficiency and bounded claim Dependency: G3 / G3A | Not Started | bar: 2026-11-09 to 2026-11-22
|  |  | M5.1 | Freeze remaining seeds, ablations, and drop-first rules | 2026-11-09 | 2026-11-10 | Thanh | Preregistered three-seed matrix and one-factor ablation order Dependency: G2A | Not Started | bar: 2026-11-09 to 2026-11-10
|  |  | M5.2 | Verify seed cache parity and seal external inputs | 2026-11-09 | 2026-11-11 | Khương | Cache-identity receipt; external labels remain sealed Dependency: G2A | Not Started | bar: 2026-11-09 to 2026-11-11
|  |  | M5.3 | Run matched QARF/QPAF seed 2 | 2026-11-11 | 2026-11-13 | Tấn Phát | Seed-2 checkpoints, predictions, telemetry and independent reviews Dependency: G2A | Not Started | bar: 2026-11-11 to 2026-11-13
|  |  | M5.4 | Run matched QARF/QPAF seed 3 | 2026-11-16 | 2026-11-18 | Tấn Phát | Seed-3 checkpoints, predictions, telemetry and independent reviews Dependency: G2A | Not Started | bar: 2026-11-16 to 2026-11-18
|  |  | M5.5 | Run retriever, fusion, and efficiency checks | 2026-11-16 | 2026-11-18 | Khương | One-factor retriever/normalization checks and efficiency report Dependency: G2A | Not Started | bar: 2026-11-16 to 2026-11-18
|  |  | M5.6 | Run feature and conditioning ablations | 2026-11-18 | 2026-11-19 | Tấn Phát | One-factor feature and query-vs-page conditioning ablation table Dependency: G2A | Not Started | bar: 2026-11-18 to 2026-11-19
|  |  | M5.7 | Aggregate three-seed robustness evidence | 2026-11-19 | 2026-11-20 | Thanh | Seed-averaged paired CI, W/T/L, stability, subgroups and errors Dependency: G2A | Not Started | bar: 2026-11-19 to 2026-11-20
|  |  | M5.8 | Test the sealed external benchmark if core evidence is safe | 2026-11-19 | 2026-11-20 | Thanh | Frozen external result or explicit not-run/inconclusive record Dependency: G2A | Deferred | bar: 2026-11-19 to 2026-11-20
|  |  | M5.9 | G3 — Robustness: is the result stable across seeds and checks? | 2026-11-20 | 2026-11-20 | Tấn Phát | GO / LIMITED-CLAIM / NO-GO / BLOCKED robustness record Dependency: Các Task M5 | Not Started | bar: 2026-11-20
|  |  | M5.10 | G3A — Generalization: bound the claim to sealed evidence | 2026-11-20 | 2026-11-20 | Thanh | PASS / INCONCLUSIVE / NEGATIVE / NOT RUN external-evidence record Dependency: Các Task M5 | Deferred | bar: 2026-11-20
|  |  | M5.11 | R5 — Sprint 5 Progress Report | 2026-11-19 | 2026-11-20 | Tấn Phát | Supervisor progress report + evidence + blockers + next sprint plan Dependency: G3 / G3A | Not Started | bar: 2026-11-19 to 2026-11-20
|  | M6 |  | Final Analysis & Thesis-Ready Research Package | 2026-11-23 | 2026-12-06 | Tấn Phát | Auditable thesis-ready evidence and reproducibility package Dependency: G4 | Not Started | bar: 2026-11-23 to 2026-12-06
|  |  | M6.1 | Verify clean checkpoint loading and inference | 2026-11-23 | 2026-11-25 | Tấn Phát | Fresh-environment load and fused-score parity within 1e-7 Dependency: G3 / G3A | Not Started | bar: 2026-11-23 to 2026-11-25
|  |  | M6.2 | Freeze the experiment ledger and provenance links | 2026-11-23 | 2026-11-25 | Thanh | Append-only links from each result to config, data, checkpoint and predictions Dependency: G3 / G3A | Not Started | bar: 2026-11-23 to 2026-11-25
|  |  | M6.3 | Finalize data and retrieval manifests | 2026-11-23 | 2026-11-26 | Khương | Dataset/OCR/cache/candidate/qrels/split/license/coverage package Dependency: G3 / G3A | Not Started | bar: 2026-11-23 to 2026-11-26
|  |  | M6.4 | Generate final research tables from the ledger | 2026-11-26 | 2026-11-30 | Thanh | Final baseline, robustness, ablation, efficiency and external tables Dependency: G3 / G3A | Not Started | bar: 2026-11-26 to 2026-11-30
|  |  | M6.5 | Produce figures, examples, and error analysis | 2026-12-01 | 2026-12-02 | Thanh | Thesis-ready plots, examples, limitations and claim checklist Dependency: G3 / G3A | Not Started | bar: 2026-12-01 to 2026-12-02
|  |  | M6.6 | Write the method and positive/negative result | 2026-11-30 | 2026-12-03 | Tấn Phát | Method/results text covering matched comparison and oracle–learned gap Dependency: G3 / G3A | Not Started | bar: 2026-11-30 to 2026-12-03
|  |  | M6.7 | Build and verify the reproducibility archive | 2026-11-27 | 2026-12-03 | Khương | Reproducibility archive, manifests, commands and fresh-hash review Dependency: G3 / G3A | Not Started | bar: 2026-11-27 to 2026-12-03
|  |  | M6.8 | Prepare thesis, presentation, and demo outlines | 2026-12-02 | 2026-12-03 | Tấn Phát | Core-first thesis/presentation/demo outline and optional-RAG decision Dependency: G3 / G3A | Not Started | bar: 2026-12-02 to 2026-12-03
|  |  | M6.9 | Run the final independent evidence audit | 2026-12-03 | 2026-12-04 | Thanh | Recomputed numbers, hashes, reload checks and final claim audit Dependency: G3 / G3A | Not Started | bar: 2026-12-03 to 2026-12-04
|  |  | M6.10 | G4 — Final Evidence: is the package defensible for submission? | 2026-12-04 | 2026-12-04 | Tấn Phát | COMPLETE / ACTIVATE BUFFER / REJECT CLAIM decision Dependency: Các Task M6 | Not Started | bar: 2026-12-04
|  |  | M6.11 | R6 — Sprint 6 Progress Report | 2026-12-03 | 2026-12-04 | Tấn Phát | Final supervisor report + evidence, claim boundary and buffer decision Dependency: G4 | Not Started | bar: 2026-12-03 to 2026-12-04
|  | B |  | Weeks 13–16 Contingency (documented gate trigger only) | 2026-12-07 | 2027-01-03 | Tấn Phát | Conditional recovery log, or record that buffer was unused Dependency: G4: kích hoạt Buffer | Contingency | bar: 2026-12-07 to 2027-01-03
|  |  | B.1 | Recover missing core evidence | 2026-12-07 | 2026-12-11 | Khương | Bounded recovery artifact with owner, authority and exit condition Dependency: G4: kích hoạt Buffer | Contingency | bar: 2026-12-07 to 2026-12-11
|  |  | B.2 | Repair compute or reproducibility failure | 2026-12-14 | 2026-12-18 | Tấn Phát | Reproduced root cause and verified repair Dependency: G4: kích hoạt Buffer | Contingency | bar: 2026-12-14 to 2026-12-18
|  |  | B.3 | Complete claim-critical seeds or ablations | 2026-12-21 | 2026-12-23 | Thanh | Gate-3 evidence or explicit stop record Dependency: G4: kích hoạt Buffer | Contingency | bar: 2026-12-21 to 2026-12-23
|  |  | B.4 | Complete essential thesis/report integration | 2026-12-28 | 2026-12-30 | Thanh | Accepted thesis/repository package and supervisor sign-off Dependency: G4: kích hoạt Buffer | Contingency | bar: 2026-12-28 to 2026-12-30
|  |  | B.5 | Optional supplementary work after core closure | 2026-12-31 | 2027-01-01 | Tấn Phát | Clearly labeled optional result or unused-time note Dependency: G4: kích hoạt Buffer | Contingency | bar: 2026-12-31 to 2027-01-01
[5 empty] | 2025-08-09 | 2025-05-10

## Proposal Traceability
Proposal → WBS Traceability & Architecture Coverage
Source: 23110035_23110060_23110062_Group01_Proposal.md ¦ Project window: 24/08/2026–13/12/2026
Proposal area | Architecture / requirement | WBS coverage | Weeks | Scope class | Implementation note
Research workflow | Literature Review → Research Question → Existing Benchmark → Reproduce Baselines → Proposed Method → Controlled Experiment → Quantitative Evaluation → Ablation → Error Analysis → Conclusion → Application Integration | 1.1–1.5, 2.1–2.5, 3.1–3.5, 4.1–4.5, 5.1–5.5, 6.1–6.5 | W1–W16 | Core research + engineering | Preserves the proposal's controlled-experimental sequence and delays substantial application work until research evidence is available.
Preprocessing / retrieval inputs | Document → Native text extraction (born-digital) / OCR fallback (scan/image) + Page rendering → Text/Page-image representations → BM25 / Dense / Visual | 2.3–2.5 | W3–W4 | Supporting engineering for research | No new OCR architecture and no benchmark construction; parser/OCR are existing components.
QARF internal architecture | Query → BM25/Dense/Visual in parallel → Candidate union → Query features + confidence features + retriever agreement → lightweight gate → Softmax αq/βq/γq → normalized fused score → final page ranking | 3.1–3.5 | W5–W8 | Main research contribution | Gate candidates: linear/regressor, shallow MLP, optional tree-based model; LLM router excluded from core experiment.
Baseline / comparison architecture | B1 BM25; B2 frozen dense retriever; B3 frozen visual retriever; B4 RRF; B5 fixed weighted fusion | 2.4–2.5, 3.2, 4.1–4.2 | W4, W6, W9–W10 | Mandatory research baselines | Fixed weights selected on validation and frozen before final test.
Application architecture | USER → Upload File → Validation → Native PDF Parser / OCR Fallback → Page Rendering → BM25/Dense/Visual → QARF/Best Method → Relevant Pages → Existing Answer Model → Answer + Evidence Metadata → Application UI | 5.1–5.5 | W13–W14 | Engineering/application | Production method is selected by the experiment decision gate; research conclusion and production choice may differ.
Evidence presentation | Display answer, source document, page, page image, retrieval score and relevant text; bbox only if parser already provides coordinates | 5.4 | W14 | Engineering/application | No new evidence-localization/region-grounding algorithm is introduced.
Benchmarks & datasets | ViDoRe primary; MMDocIR secondary/external; DocVQA + MP-DocVQA optional downstream; ViOCRVQA + ReceiptVQA application validation; small PDFs for demo only | 2.1, 4.5, 5.5 | W3, W12, W14 | Evaluation/data | Explicitly no custom Vietnamese benchmark and no large-scale annotation task.
Experiment matrix | E1 individual retrievers; E2 static fusion; E3 QARF; E4 MMDocIR external validation; E5 downstream QA if time permits | 4.1–4.5, 5.5 | W9–W14 | Research evaluation | E1–E3 are core; E4 conditional on compute; E5 is nice-to-have.
Ablation matrix | A1 no adaptive gating; A2 no visual; A3 no lexical; A4 query features only; A5 retrieval features only | 4.3 | W11 | Research evaluation | A1 and A2 are mandatory; A3–A5 only if schedule/compute permits.
Reproducibility & governance | Record experiment ID, timestamp, dataset/model/checkpoint/preprocessing/Top-K/fusion/hyperparameters/seed/hardware/runtime/metrics; citation and license audit | 1.4–1.5, 6.2–6.3 | W2, W15 | Cross-cutting | Traceability is maintained from claims to sources and from experiments to reproducible configurations.
Explicitly out of scope | New OCR/VLM/LLM architecture; large OCR fine-tuning; new multimodal generator; new grounding algorithm; new hallucination detector; agentic RAG; benchmark construction; large-scale annotation | Guardrail across all WPs | W1–W16 | Excluded | These items are intentionally not scheduled, preventing the WBS from drifting back to the older proposal.
16-Week Calendar (fixed from 24/08/2026)
Week | Start | End | Proposal focus | Primary WBS
W1 | 2026-08-24 | 2026-08-30 | Freeze scope, RQs, benchmark and mandatory experiments | 1.1–1.2
W2 | 2026-08-31 | 2026-09-06 | Literature review and evidence matrix | 1.3–1.5
W3 | 2026-09-07 | 2026-09-13 | ViDoRe acquisition, evaluation harness and preprocessing | 2.1–2.3
W4 | 2026-09-14 | 2026-09-20 | BM25, dense and visual baselines | 2.4–2.5
W5 | 2026-09-21 | 2026-09-27 | Score/overlap/confidence and error inspection | 3.1
W6 | 2026-09-28 | 2026-10-04 | RRF, fixed fusion and score normalization | 3.2
W7 | 2026-10-05 | 2026-10-11 | QARF feature extraction and gating model | 3.3–3.4
W8 | 2026-10-12 | 2026-10-18 | QARF prototype and validation experiments | 3.5
W9 | 2026-10-19 | 2026-10-25 | Final individual baseline experiments | 4.1
W10 | 2026-10-26 | 2026-11-01 | Static fusion vs QARF | 4.2
W11 | 2026-11-02 | 2026-11-08 | Ablation studies | 4.3
W12 | 2026-11-09 | 2026-11-15 | MMDocIR (if feasible), statistics, error analysis and decision gate | 4.4–4.5
W13 | 2026-11-16 | 2026-11-22 | Ingestion, API and indexing | 5.1–5.2
W14 | 2026-11-23 | 2026-11-29 | Answerer integration, Vietnamese datasets and frontend | 5.3–5.5
W15 | 2026-11-30 | 2026-12-06 | End-to-end testing, figures/tables, reproducibility and citation audit | 6.1–6.3
W16 | 2026-12-07 | 2026-12-13 | Final report, presentation, demo and defense rehearsal | 6.4–6.5

## Notes
Milestone Notes
Gate | Timing | Decision question | Status | Meaning
G1 | End of W2 | Can the team trust the starting evidence and frozen protocol? | Not Started | Planned work has not begun
G2 | End of W6 | Does learned QPAF outperform matched learned QARF? | In Progress | Work is actively underway
G3 | Around W10 | Is the result stable across seeds, ablations and robustness checks? | Blocked | A prerequisite or approval is unresolved
G4 | End of W12 | Is the evidence complete and defensible for submission? | Done | Repository evidence fulfills the row
|  |  | Deferred | Optional work is postponed
|  |  | Contingency | Runs only after a documented gate trigger
Protocol notes
G2 evaluates learned QPAF against matched learned QARF. The full baseline matrix belongs to M4.
If QPAF is weak or unstable, retain the negative result, diagnose it, and stop unnecessary expensive runs.
Dataset role, primary metric, seed policy and baseline roster stay generic until protocol freeze.
Weeks 13–16 are contingency only and require a documented unmet core gate.
Statuses are preserved from the source snapshot dated 11/09/2026.
Sources
Plan and status source: PROJECT_MILESTONE.xlsx (snapshot dated 11/09/2026).
Layout reference: Mẫu phân công.xlsx (visual structure only).